## Sheet1
No. | Product Deliverables | Task | Phạm Huy Hoàng | Nguyễn Thanh Bình | Nguyễn Quốc Huy | Đỗ Minh Đạt | Unit | Size
1 | Report1 - Introduction | Project Information | O
|  | Introduction |  |  | O
|  | Current Roll Call System |  | O
|  | Proposed Solution | O
|  | Functional Requirement | O
|  | Roles and Responsibility | O
2 | Report2- Software Project Management Plan | Problem Definition |  |  | O
|  | Project organization | O
|  | Project management plan | O
|  | Coding Convention |  | O
3 | Report 3- Software Requirement Specification | User Requirement Specification | O
System Requirement Specification
|  | External Interface Requirements |  | O
Functional Requirement
|  | Instructor Requirement |  | O
|  | Admin Requirement | O
|  | Staff Requirement |  |  | O
|  | System Requirement | O
|  | Student Requirement |  |  | O
|  | Guest Requirement | O
Non-functional Requirement
|  | Reliability |  |  | O
|  | Availability |  | O
|  | Sercurity |  |  | O
|  | Performance | O
|  | Conceptual Diagram | O
| Report 4- Software Design Description | Design Overview | O
|  | System Architectural Design | O
|  | Component Diagram | O
|  | Class diagram | O
Class specification (states, behaviors)
|  | RollCall |  |  | O
|  | Subject |  |  | O
|  | SubjectType |  |  | O
|  | Major |  |  | O
|  | Class |  |  | O
|  | StudySession |  |  | O
|  | Instructor |  |  | O
|  | Semester |  |  | O
|  | Student |  |  | O
|  | Staff |  |  | O
|  | User |  |  | O
|  | Role |  |  | O
|  | StudentImage |  |  | O
|  | StudentAttendance |  |  | O
|  | AttendanceLog |  |  | O
|  | LogType |  |  | O
|  | LogImage |  |  | O
|  | Request |  |  | O
|  | RequestImage |  |  | O
Detailed Description of Components
Sequence Diagram
|  | Add Image for Single Student | O
|  | Add Image for Manu Students | O
|  | Delete Student Image | O
|  | Create Account | O
|  | Configure System | O
|  | Face Detection | O
|  | Face Recognition | O
|  | Auto Free Storage Space | O
|  | Auto Active Roll Call | O
|  | Add Roll Call | O
|  | Edit Roll Call | O
|  | Import Student List |  |  | O
|  | Export Report |  |  | O
|  | Add Student |  |  | O
|  | Add Class |  |  | O
|  | Edit Class |  |  | O
|  | Add Subject |  |  | O
|  | Edit Subject |  |  | O
|  | Take Attendance Auto |  | O
|  | Take Attendance Manual |  | O
|  | View Roll Call Detail |  | O
|  | Report Roll Call by Class |  | O
|  | Check Present Rate |  | O
Database Design
|  | Entity Relationship Diagram | O
|  | Data Dictionary |  |  | O
Algorithms
|  | Face Detection | O
|  | Face Recognition | O
5 | Report 5 - Software Implementation and Test Document | Setup Environtment
Attendance Checking (Web)
|  | Check Attendance Auto (Web) | O |  |  |  |  | 3
|  | Check Attendance Manual (Web) | O |  |  |  |  | 3
|  | View Roll Call Detail (Web) | O |  |  |  |  | 2
Attendance Checking (Mobile)
|  | Login |  | O |  |  |  | 1
|  | Show Current Roll Call |  | O |  |  |  | 2
|  | Check Attendance Auto |  | O |  |  |  | 4
|  | Check Attendance Manual |  | O |  |  |  | 3
|  | View Roll Call Detail |  | O |  |  |  | 2
|  | Show Current Roll Call (Offline) |  | O |  |  |  | 2
|  | Check Attendance Offline + Sync Data |  | O |  |  |  | 4
Roll Call Management
|  | Add Roll Call |  |  | O |  |  | 3
|  | Edit Roll Call |  |  | O |  |  | 2
Study Session Management
|  | Add Study Session |  |  | O |  |  | 1
|  | Change Session Time |  |  | O |  |  | 2
|  | Change Session Instructor |  |  | O |  |  | 2
Face Detection & Recognition
|  | Face Detection | O |  |  |  |  | 4
|  | Face Recognition | O |  |  |  |  | 4
|  | Add Image for Single Student | O |  |  |  |  | 2
|  | Add Image using Log Images | O |  |  |  |  | 2
Web Serivce
|  | Login Service |  |  | O |  |  | 1
|  | Roll Call Info Service |  | O |  |  |  | 3
|  | Check Attendance Auto Service | O |  |  |  |  | 3
|  | Check Attendance Manual Service |  | O |  |  |  | 3
Attendance Report
|  | Roll Call List Report | O |  |  |  |  | 3
|  | Student List for Final Exam |  |  | O |  |  | 3
|  | Single Student in Semester Report |  |  | O |  |  | 3
Check own Attendance Rate
|  | View Attendance of Learned Course |  | O |  |  |  | 2
|  | View Attendance of Learning Course |  | O |  |  |  | 2
Teaching Calendar
|  | Show Teaching Calendar | O |  |  |  |  | 3
|  | Sync with Google Calendar | O |  |  |  |  | 4
Request Management
|  | Create Request |  |  | O |  |  | 2
|  | Upload Request |  |  | O |  |  | 2
|  | Accept Request |  |  | O |  |  | 1
|  | Deny Request |  |  | O |  |  | 1
Account Management
|  | Manage Account | O |  |  |  |  | 1
|  | Login/Logout | O |  |  |  |  | 1
|  | Change Password | O |  |  |  |  | 1
|  | Student Management |  |  | O |  |  | 2
|  | Instructor Management |  |  | O |  |  | 2
|  | Class Management |  |  | O |  |  | 1
|  | Subject Management |  |  | O |  |  | 1
|  | Semester Management |  |  | O |  |  | 1
|  | DB diagrams | O
Write Test case
|  | Manage Roll Call |  |  | O
|  | Manage Student Image | O
|  | Check Attendance |  | O
|  | Attendance Report |  |  | O
|  | Manage Teaching Calendar | O
|  | Manage Study Session |  | O
|  | Check own Attendance Rate |  | O
Perform Testing
|  | Manage Roll Call |  |  | O
|  | Manage Student Image | O
|  | Check Attendance |  | O
|  | Attendance Report |  |  | O
|  | Manage Teaching Calendar | O
|  | Manage Study Session |  | O
|  | Check own Attendance Rate |  | O
6 | Report 6 - Software User's Manual | Installation Guide | O
User’s Guide
|  | Login | O
|  | Admin - Add Image for student | O
|  | Staff - Create Roll Call |  |  | O
|  | Instructor - Check Attendance (Mobile) |  | O
|  | Instructor - Check Report |  | O
User Notice
|  | Image Data Notice | O
|  | Position & Angle Notice | O
|  | Other Notice | O
Notes
No. | Function Types | Function Point Size
1 | Insert, Delete, Update, Simple Search, Login, Register, simple function or simple query on one table | 1
2 | Computed functions or joined query | 2
3 | Complex functions or multiple subquery | 3
4 | Constraint process and data integrity | 4
5 | Functions with implementing algorithms | 5
Note on C2: phuong: Each row is a topic in project document. Do not have more than 15 rows in each product deliverable. Content in this template is used for reference only and it is vary in each project
Note on D2: phuong: Only one member in line, who has main repsonsibilty in this task
Note on C13: phuong: Use bold format for tasks which have sub-tasks
Note on C14: phuong: Use Indent for sub-tasks